## Itemized Proposal
ITEMIZED PROPOSAL
FORT WAYNE ALLEN-COUNTY AIRPORT AUTHORITY
FORT WAYNE INTERNATIONAL AIRPORT (FWA)
FORT WAYNE INDIANA
EXTEND TAXIWAY G AND CONSTRUCT TAXILANE K1
BASE BID
[6 empty] | Project Milestone: | Addendum No.1
[6 empty] | Date: | 2026-06-24
ITEM NO. | SPECIFICATION | DESCRIPTION OF ITEM | UNIT | QUANTITY | UNIT PRICE (WORDS) | UNIT PRICE | EXTENSION
STANDARD PAY ITEMS
1 | C-100-14.1 | CONTRACTOR QUALITY CONTROL PROGRAM | LS | 1
2 | C-102-5.1 | INSTALL, MAINTAIN, AND REMOVE FILTER SOCK PERIMETER PROTECTION | LFT | 1370
3 | C-102-5.2 | INSTALL, MAINTAIN, AND REMOVE INLET PROTECTION | EA | 37
4 | C-102-5.3 | INSTALL, MAINTAIN AND REMOVE CONSTRUCTION ENTRANCE & TEMPORARY HAUL ROUTE | SYD | 790
5 | C-102-5.4 | INSTALL, MAINTAIN, AND REMOVE CONCRETE WASHOUT | EA | 1
6 | C-105-7.1 | MOBILIZATION | LS | 1 |  |  |  |  | SUBMITTED BY:
7 | C-105-7.2 | ENGINEER'S FIELD OFFICE | MO | 4 |  |  |  |  | TITLE:
8 | P-101-5.1 | PAVEMENT REMOVAL (4" AGGREGATE SHOULDER, AVG. DEPTH) | SYD | 200 |  |  |  |  | ADDRESS:
9 | P-101-5.2 | PAVEMENT REMOVAL - PCCP (12" PCCP WITH 6" AGG. BASE) | SYD | 670
10 | P-101-5.3 | PAVEMENT REMOVAL - PCCP (16" PCCP, AVG. DEPTH) | SYD | 230 |  |  |  | END OF ITEMIZED PROPOSAL
11 | P-101-5.4 | PAVEMENT REMOVAL - HMA (7.5"± HMA ON 6"± BASE, AVG. DEPTH) | SYD | 2500
12 | P-101-5.5 | PAVEMENT REMOVAL - HMA (5" HMA ON 12" PCCP ON 6" AGG. BASE, AVG. DEPTH) | SYD | 2000
13 | P-101-5.6 | COLD MILLING - 2" DEPTH | SYD | 370
14 | P-101-5.7 | REMOVE FENCE - 10 FT CHAIN-LINK | LFT | 810
15 | P-101-5.8 | REMOVE WATER LINE - 12" DIA. MAIN | LFT | 1040
16 | P-101-5.9 | REMOVE WATER LINE - 8" DIA. SERVICE | LFT | 230
17 | P-101-5.10 | CUT, CAP AND FILL ABANDONED WATER LINE - 12" DIA. MAIN | LFT | 60
18 | P-101-5.11 | REMOVE FIRE HYDRANT | EA | 2
19 | P-101-5.12 | REMOVE UPTO 6-INCH DIA. HDPE | LFT | 50
20 | P-101-5.13 | REMOVE UPTO 15-INCH DIA. CMP | LFT | 150
21 | P-101-5.14 | REMOVE UPTO 30-INCH DIA. RCP STORM SEWER PIPE | LFT | 1300
22 | P-101-5.15 | REMOVE STORM STRUCTURE (UPTO 48-INCH DIA.) | EA | 6
23 | P-101-5.16 | REMOVE UNDERDRAIN PIPE, 6" DIA. PVC | LFT | 1050
24 | P-101-5.17 | REMOVE UNDERDRAIN CLEANOUT | EA | 4
25 | P-101-5.18 | REMOVE UNDERGROUND DIRECT EARTH BURIED ELECTRIC CABLING | LFT | 320
26 | P-101-5.19 | REMOVE UNDERGROUND DIRECT EARTH BURIED COMMUNICATION CABLING | LFT | 3310
27 | P-101-5.20 | REMOVE UNDERGROUND FAA COMMUNICATION CABLING | LFT | 1290
28 | P-101-5.21 | REMOVE FAA COMMUNICATION DUCT BANK AND CABLING | LFT | 490
29 | P-101-5.22 | REMOVE 4" STEEL GAS MAIN (ABANDONED) | LFT | 1010
30 | P-101-5.23 | REMOVE 2" PVC CONDUIT AND CABLE | LFT | 680
31 | P-101-5.24 | REMOVE 2" CONCRETE ENCASED PVC CONDUIT AND CABLING | LFT | 90
32 | P-101-5.25 | REMOVE ROAD SIGN | EA | 1
33 | P-101-5.26 | REMOVE 4" - 4 WAY CONCRETE ENCASED DUCT BANK | LFT | 110
34 | P-101-5.27 | REMOVE ELECTRICAL HANDHOLE | EA | 5
35 | P-101-5.28 | REMOVE UTILITY PEDESTAL | EA | 3
36 | P-101-5.29 | REMOVE TAXIWAY FIXTURE, BASE MOUNTED | EA | 13
37 | P-101-5.30 | REMOVE RETROREFLECTOR | EA | 5
38 | P-101-5.31 | REMOVE AIRFIELD GUIDANCE SIGN | EA | 1
39 | P-151-4.1 | CLEARING AND GRUBBING | AC | 1.2
40 | P-152-4.1 | UNCLASSIFIED EXCAVATION | CYD | 11233
41 | P-152-4.2a | BORROW EXCAVATION (ON-SITE SPOILS) | CYD | 2000
42 | P-154-5.1 | SUBBASE COURSE (INDOT NO. 53'S) | CYD | 3140
43 | P-156-8.1 | CEMENT TREATED SUBGRADE | SYD | 16710
44 | P-156-8.2 | CEMENT | TON | 560
45 | P-307-7.1 | CEMENT-TREATED PERMEABLE BASE COURSE (6" DEPTH) | SYD | 6690
46 | P-307-7.2 | BOND BREAKER | SYD | 6690
47 | P-501-8.1 | PORTLAND CEMENT CONCRETE PAVEMENT (12" DEPTH) | SYD | 3510
48 | P-501-8.2 | PORTLAND CEMENT CONCRETE PAVEMENT (16" DEPTH) | SYD | 6140
49 | P-501-8.3 | REINFORCEMENT FOR ODD SHAPED PANELS | SYD | 1120
50 | P-605-5.1 | JOINT SEALING FILLER | LFT | 10700
51 | P-620-5.1a | REMOVAL OF EXISTING PAVEMENT MARKINGS | SFT | 1380
52 | P-620-5.1b | SURFACE PREPARATION FOR APPLICATION OF NEW PAVEMENT MARKINGS | SFT | 3910
53 | P-620-5.2a | PAVEMENT MARKING - YELLOW (FULL APPLICATION) | SFT | 2990
54 | P-620-5.2b | PAVEMENT MARKING - BLACK (FULL APPLICATION) | SFT | 2300
55 | P-620-5.3 | REFLECTIVE MEDIA | LBS | 260
56 | P-620-5.4 | PAVEMENT MARKING - YELLOW (HALF APPLICATION) | SFT | 2990
57 | F-162-5.1 | CHAIN-LINK SECURITY FENCE, 10 FT WITH BARBED WIRE | LFT | 920
58 | D-701-5.1 | STORM SEWER PIPE, 18" RCP, CLASS IV | LFT | 670
59 | D-701-5.2 | STORM SEWER PIPE, 24" RCP, CLASS IV | LFT | 830
60 | D-701-5.3 | STORM SEWER PIPE, 30" RCP, CLASS IV | LFT | 770
61 | D-701-5.4 | STORM SEWER PIPE, 36" RCP, CLASS IV | LFT | 160
62 | D-701-5.5 | STORM SEWER PIPE, 42" RCP, CLASS IV | LFT | 230
63 | D-701-5.6 | STORM SEWER PIPE, 48" RCP, CLASS IV | LFT | 270
64 | D-705-5.1 | PERFORATED UNDERDRAIN PIPE, 6-INCH PVC | LFT | 2780
65 | D-705-5.2 | UNDERDRAIN CLEANOUT | EA | 14
66 | D-751-5.1 | STORM STRUCTURE, INLET, INDOT TYPE A | EA | 2
67 | D-751-5.2 | STORM STRUCTURE, MANHOLE, INDOT TYPE E | EA | 2
68 | D-751-5.3 | STORM STRUCTURE, MANHOLE, INDOT TYPE C | EA | 10
69 | D-751-5.4 | STORM STRUCTURE, MANHOLE, INDOT TYPE J | EA | 9
70 | D-751-5.5 | STORM STRUCTURE, MANHOLE, INDOT TYPE K | EA | 4
71 | D-751-5.6 | STORM STRUCTURE, MANHOLE, WATER QUALITY STRUCTURE | EA | 1
72 | T-901-5.1 | HYDROMULCH SEEDING | KSFT | 670
73 | L-108-5.1 | NO. 8 AWG, 5 KV, L-824, TYPE C CABLE, INSTALLED IN DUCT BANK OR CONDUIT | LFT | 2100
74 | L-108-5.2 | NO. 6 AWG, SOLID, BARE COPPER COUNTERPOISE WIRE, INSTALLED ABOVE THE DUCT BANK OR CONDUIT | LFT | 1910
75 | L-108-5.3 | NO. 19 AWG, 50 PAIR, COPPER CONTROL CABLE, OWNER-FURNISHED, INSTALLATION ONLY | LFT | 1270
76 | L-110-5.1 | ELECTRICAL CONDUIT, 1W-2" SCH 40 PVC | LFT | 50
77 | L-110-5.2 | CLSM ENCASED ELECTRICAL CONDUIT, 1W-2” SCH 40 PVC | LFT | 1660
78 | L-110-5.3 | CONCRETE ENCASED ELECTRICAL CONDUIT, 1W-2” SCH 40 PVC | LFT | 240
79 | L-110-5.4 | CONCRETE ENCASED ELECTRICAL/COMMUNICATION CONDUIT, 2W-4" SCH 40 PVC | LFT | 530
80 | L-110-5.5 | CONCRETE ENCASED COMMUNICATION CONDUIT, 2W-2" SCH 40 PVC | LFT | 1340
81 | L-110-5.6 | SAND ENCASED ELECTRICAL CONDUIT, 2W-4" SCH 40 PVC | LFT | 850
82 | L-110-5.7 | SAND ENCASED COMMUNICATION CONDUIT, 1W-4" SCH 40 PVC | LFT | 369
83 | L-115-5.1 | 4' X 4' X 4' AIRPORT RATED MANHOLE | EA | 2
84 | L-115-5.2 | L-867D, CLASS 1A, BASE CAN WITH SOLID LID COVER | EA | 3
85 | L-125-5.1 | LED GUIDANCE SIGN, SIZE 3, 2 MODULE, L-858(L), STYLE 2 | EA | 2
86 | L-125-5.2 | LED GUIDANCE SIGN, SIZE 3, 3 MODULE, L-858(L), STYLE 2 | EA | 1
87 | L-125-5.3 | NON-ILLUMINATED TWY END SIGN, SIZE 3, 2 MODULE, L-858, STYLE 4 | EA | 2
88 | L-125-5.4 | NON-ILLUMINATED MOVEMENT SIGN, SIZE 3, 2 MODULE, L-858, STYLE 4 | EA | 1
89 | L-125-5.5 | NON-ILLUMINATED STOP SIGN | EA | 1
90 | L-125-5.6 | GUIDANCE SIGN PANEL REPLACEMENT | EA | 2
91 | L-125-5.7 | LED MEDIUM INTENSITY TAXIWAY EDGE LIGHT, L-861T(L) IN TURF | EA | 19
92 | L-125-5.8 | STAKE MOUNTED RETROREFLECTOR, L-853 | EA | 24
93 | L-125-5.9 | SURFACE MOUNTED RETROREFLECTOR, L-853 | EA | 5
94 | L-125-5.13 | BASE CAN WITH LID, L-867B, CLASS 1A | EA | 6
95 | IST-01-5.1 | INDOT 401, QC/QA HMA, 3, 58E-28, SURFACE COURSE, 12.5 MM | TON | 970
96 | IST-01-5.2 | INDOT 401, QC/QA HMA, 3, 58E-28, BASE COURSE, 19.0 MM | TON | 1880
97 | LST-01-5.1 | ELECTRICAL HANDHOLE, POLYMER CONCRETE, 24”x36”x36” | EA | 10
98 | MST-01-3.1 | INSTALL, MAINTAIN, AND REMOVE LOW PROFILE CONSTRUCTION BARRICADES | LFT | 300
99 | MST-01-3.2 | INSTALL, MAINTAIN, AND REMOVE TAXIWAY CLOSURE CROSS | EA | 1
100 | MST-01-3.3 | INSTALL, MAINTAIN, AND REMOVE CONSTRUCTION SIGN | EA | 12
101 | MST-01-3.4 | INSTALL, MAINTAIN, AND REMOVE TEMPORARY FENCE | LFT | 1590
102 | MST-01-3.5 | INSTALL, MAINTAIN, AND REMOVE TEMPORARY GATE | EA | 1
103 | MST-01-3.6 | OBSCURE GUIDANCE SIGN | EA | 7
104 | MST-01-3.7 | OBSCURE EDGE LIGHT | EA | 46
105 | MST-01-3.8 | INSTALL, MAINTAIN, AND REMOVE TEMPORARY SILT FENCE BARRIER | LFT | 1775
106 | MST-02-4.1 | CONSTRUCTION ENGINEERING | LS | 1
107 | MST-05-5.1 | 12" HDPE PRESSURE UTILITY PIPING, WATER MAIN | LFT | 1580
108 | MST-05-5.2 | 8" HDPE PRESSURE UTILITY PIPING, WATER SERVICE | LFT | 60
109 | MST-05-5.3 | FIRE HYDRANT ASSEMBLY TYPE III WITH GUARD BOLLARDS | EA | 2
110 | MST-05-5.4 | 12" X 12" X12" DUCTICLE IRON TEE | EA | 2
111 | MST-05-5.5 | 12" X 12" X 8" DUCTILE IRON REDUCING TEE | EA | 2
112 | MST-05-5.6 | 12" X 12" DUCTILE IRON ELBOW | EA | 2
113 | MST-05-5.7 | 8" X 8" X 2" DUCTILE IRON REDUCING TEE | EA | 1
114 | MST-05-5.8 | WATER MAIN CONNECTION (CONNECTION TO EXISTING WATER MAIN) | EA | 2
115 | MST-05-5.9 | TEST RISER (TEMPORARY) | EA | 1
116 | MST-05-5.10 | TEMPORARY BLOW-OFF VALVE | EA | 2
117 | MST-05-5.11 | 12" RESILIENT SEAT GATE VALVE AND BOX WITH ADAPTER | EA | 6
118 | MST-05-5.12 | 8" RESILIENT SEAT GATE VALVE AND BOX WITH ADAPTER | EA | 2
119 | MST-05-5.13 | 10-INCH SCHEDULE 40 CASING PIPE | LFT | 490
120 | MST-05-5.14 | 8 INCH, TYPE PVC SDR 35 (SANITARY SEWER LINE) | LFT | 580
121 | MST-05-5.15 | RESHAPE SANITARY SEWER FLOWLINE FOR NEW CONNECTION | LS | 1
122 | MST-05-5.17 | SANITARY SEWER STRUCTURE, 48" SANITARY MANHOLE | EA | 3
131 | MST-01-3.11 | INSTALL, MAINTAIN, AND REMOVE TYPE III BARRICADES WITH ROAD CLOSURE SIGN | LFT | 20
STANDARD PAY ITEMS SUBTOTAL =
UNDISTRIBUTED ITEMS
123 | P-152-4.2b | BORROW EXCAVATION (ON-SITE STOCKPILE) (UNDISTRIBUTED) | CYD | 2619
124 | P-152-4.3 | UNDERCUT UNSUITABLE MATERIAL (UNDISTRIBUTED) | CYD | 1240
125 | P-152-4.4 | SPECIAL SUBGRADE TREATMENT (UNDISTRIBUTED) | CYD | 620
126 | L-125-5.11 | SPARE PARTS (ALLOWANCE) | ALLOW | 1 | TEN THOUSAND AND 00/100 | 10000 | 10000
127 | MST-01-3.10 | TEMPORARY HANGAR SECURITY FENCE (ALLOWANCE) | ALLOW | 1 | TWENTY FIVE THOUSAND AND 00/100 | 25000 | 25000
128 | MST-03-3.1 | PROJECT SECURITY (ALLOWANCE) | ALLOW | 1 | TWO-HUNDRED FORTY FIVE THOUSAND AND 00/100 | 245000 | 245000
129 | MST-04-5.1 | HAUL ROUTE REPAIR (ALLOWANCE) | ALLOW | 1 | SEVENTY FIVE THOUSAND AND 00/100 | 75000 | 75000
130 | MST-05-5.16 | ADJUST SANITARY STRUCTURE TO GRADE (ALLOWANCE) | ALLOW | 1 | EIGHT THOUSAND AND 00/100 | 8000 | 8000
132 | T-901-5.2 | TEMPORARY HYDROMULCH SEEDING (UNDISTRIBUTED) | KSFT | 670
UNDISTRIBUTED ITEMS SUBTOTAL =
BASE BID TOTAL =
END OF BASE BID ITEMIZED PROPOSAL

## Itemized Proposal-Add Alt 1
ITEMIZED PROPOSAL
FORT WAYNE ALLEN-COUNTY AIRPORT AUTHORITY
FORT WAYNE INTERNATIONAL AIRPORT (FWA)
FORT WAYNE INDIANA
EXTEND TAXIWAY G AND CONSTRUCT TAXILANE K1
ADDITIVE ALTERNATE NO.1
[6 empty] | Project Milestone: | Addendum No.1
[6 empty] | Date: | 2026-06-24
ITEM NO. | SPECIFICATION | DESCRIPTION OF ITEM | UNIT | QUANTITY | UNIT PRICE (WORDS) | UNIT PRICE | EXTENSION
STANDARD PAY ITEMS
1001 | P-101-5.32 | REMOVE CABLE FROM CONDUIT | LFT | 5000
1002 | L-108-5.1 | NO. 8 AWG, 5KV, L-824, TYPE C CABLE, INSTALLED IN DUCT BANK OR CONDUIT | LFT | 5000
1003 | L-125-5.10 | INSTALL SALVAGED HIRL FIXTURE ON NEW BASE IN PAVED SHOULDER | EA | 10
1004 | L-125-5.11 | INSTALL SALVAGED MITL FIXTURE ON NEW BASE IN PAVED SHOULDER | EA | 15
1005 | MST-01-3.1 | INSTALL, MAINTAIN, AND REMOVE LOW PROFILE CONSTRUCTION BARRICADES | LFT | 650
1006 | MST-01-3.7 | OBSCURE EDGE LIGHT | EA | 67
1007 | MST-01-3.9 | INSTALL, MAINTAIN, AND REMOVE RUNWAY CLOSURE CROSS | EA | 2 |  |  |  | SUBMITTED BY:
STANDARD PAY ITEMS SUBTOTAL =
UNDISTRIBUTED ITEMS
1008 | P-101-5.33 | REMOVE ELEVATED HIRL OR MITL ASEEMBLY IN PAVED SHOULDER, SALAVGE FIXTURE (UNDISTRIBUTED) | EA | 25
1009 | MST-03-3.2 | PROJECT SECURITY (ADDITIVE ALTERNATE NO.1) (ALLOWANCE) | ALLOW | 1 | SIXTY THOUSAND AND 00/100 | 60000 | 60000
UNDISTRIBUTED ITEMS SUBTOTAL =
ADDITIVE ALTERNATE NO.1 TOTAL =
END OF ADDITIVE ALTERNATE NO.1 ITEMIZED PROPOSAL
SUBMITTED BY:
TITLE:
ADDRESS: